## TIG Summary
TIG Program Reserve as of May 1st, 2011
714414
Status | Year | Focus Technologies | Initial Approved Budget |  | Revised Budget | Spent in FY 2004 (July 03-July 04) | Spent in FY 2005 (July 04-July 05) | Spent in FY 2006 (July 05-July 06) | Spent in FY 2007 (July 06-July 07) | Spent in FY 2008 (July 07-June 08) | Spent in FY 2009 (July 08-June 09) | Spent in FY 2010 (July 09-April 10) | Spent in FY11 (July 10-Mar 11) | Current Remaining Budget | Projected Costs in FY 2011 | Projected Costs in FY 2009 | Projected Costs in FY 2010 | Cost Remaining in FY 2011 (Projected - Spent) | Focus Technology $ Programed beyond FY 10 | Returned funds in 2010/2011 | Additional Info
Active | 2005 | MDSS | 96700 | [5 empty] | -12341 | -15701 | -19041.87 | -10641 | -1702 | 37273.13 | -1702 |  |  | 0 | 0 | 0 | Closed
Active | 2005 | PCPS | 96625 | [5 empty] | -7042 | -12392 | -1262.35 | 0 | 0 | 75928.65 | -9000 |  |  | -9000 | 66928.65 | 66928.65 | Awaiting a closeout meeting
Closed | 2006 | SPMT's | 85150 | [5 empty] | na | -28056 | -10775.72 | -38 | -4109 | 42171.28 | -4109 |  |  | 0 | 0 | 0 | Closed
Closed | 2006 | AMG | 83050 | [5 empty] | na | -18034 | -2181.66 | -2969 | 0 | 59865.34 | 0 |  |  | 0 | 59865.34 | 59865.34 | Awaiting a closeout meeting
Active | 2007 | LRS | 75000 | [5 empty] | na | na | -2768.29 | -2577 | -1299 | 68355.71 | -19000 |  |  | -17701 | 49355.71 |  | In progress…
Active | 2007 | SR | 89650 | [5 empty] | na | na | -43425.44 | -779 | -12937 | 32508.56 | -23350 |  |  | -10413 | 9158.56 |  | In progress…
Active | 2008 | URED | 38100 | [5 empty] | na | na | 0 | -8388 | -8448 | 21264 | -21200 |  |  | -12752 | 64 |  | In progress…
Active | 2008 | GCED | 41850 | [5 empty] | na | na | 0 | -3064 | -3038 | 35748 | -14850 |  |  | -11812 | 20898 |  | In progress…
Active | 2008 | EPGT | 37900 | [5 empty] | na | na | 0 | -5083 | -3555 | 29262 | -14000 |  |  | -10445 | 15262 |  | In progress…
Active | 2009 | TowPlow | 38100 | [5 empty] | na | na |  | 0 | -11016 | 27084 | -26500 |  |  | -15484 | 584 |  | In progress…
Active | 2009 | Towing and Recovery | 40000 | s |  |  |  |  | na | na |  | 0 | 0 | 40000 | -10000 |  |  | -10000 | 30000 |  | In progress…
Active | 2010 | New Bridge Material Design Options | 40000 | s | [9 empty] | 40000 | -10000 |  |  | -10000 | 30000 |  | In progress…
Active | 2010 | New Pavement Evaluation Tools | 40000 | s | [9 empty] | 40000 | -10000 |  |  | -10000 | 30000 |  | In progress…
Active | 2010 | Sequential Barricade Warning Light System | 40000 | s | [9 empty] | 40000 | -10000 |  |  | -10000 | 30000 |  | In progress…
| 2011 |  | 10000 | s |  |  |  |  | na | na |  | na | 0 | 10000 | -10000 |  |  | -10000 | 0 |  | In progress…
| 2011 |  | 10000 | s | [7 empty] | na | 0 | 10000 | -10000 |  |  | -10000 | 0
| 2011 |  | 10000 | s | [7 empty] | na | 0 | 10000 | -10000 |  |  | -10000 | 0
| 2011 | AST (non-focus tech) | 0 | [9 empty] | 0 | 0 | 0 |  |  | 0 | 0
|  | TIG Gen (Other Outside Support) | 80000 | [5 empty] | -21034 | -29643 | -43803.57 | -76313.21 | -24889 | 55111 | -85000 |  |  | -60111 |  | 0
|  | Staff(Overhead & Benefits) | 40000 | [5 empty] | -48926 | -40000 | -6000 | -34627 | -32332 | 7668 | -40000 |  |  | -7668 |  | 0
[9 empty] | -89343 | -143826 | -129258.9 | -144479.21 | -103325 | 682239.67 | -328711 |  |  | -225386 | 342116.26 | 126793.99
[14 empty] | Program Reserve at FY 10: | 534414
Additions
|  | Current Program Money Total | 714414 | [10 empty] | Collected Funds (FY 11): | 180000
|  | Estimated Total FY 11: | -328711
[14 empty] | (YTD) FY 11 Expenses: | -103325
|  | Estimated Reserve EOY 2011 | 385703
|  | Deductions | [11 empty] | Current Program Money Total: | 714414
|  | Focus Techs' $ Programed | 342116.26
|  | Projectec Returned Funds in 2011 | -126793.99
|  | Sum Deductions: | 215322.27
|  | Est Reserve After FY 2011 | 170380.73

## MDSS
MDSS Budget | [7 empty] | 2007-09-01
|  |  |  | Development | Delivery |  |  | Development | Delivery | Development | Delivery
Tasks |  |  | Number | Cost | Cost | Start | End | 2007 | 2007 | 2008 | 2008 | Total Spent | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice | Amount | Date of Invoice
Enhanced PowerPoint Presentation | [5 empty] | 2007-02-01 | 2007-04-30 | 0 | 0 |  |  | 0
| Writing/Editing (including approvals) |  |  | 8000 |  | 2007-02-01 | 2007-03-31 | 8000 | 0 |  |  | 0
| Graphic Design (including approvals) |  |  | 2000 |  | 2007-02-01 | 2007-04-30 | 2000 | 0 |  |  | 0
| Talking Points Writing/Editing |  |  | 300 |  | 2007-02-01 | 2007-04-30 | 300 | 0 |  |  | 0
| Meetings/Events | [6 empty] | 0 | 0 |  |  | 0
|  | Team member travel (1 Person @ $1000 per presentation) | 3 |  | 3000 | 2007-06-01 | 2008-03-31 |  |  | 0 | 3000 | 0
| FHWA MDSS RoadShow | [6 empty] | 0 | 0 |  |  | 0
|  | Team member travel (1 person @ $1000 per meeting) | 5 |  | 5000 | 2007-03-01 | 2008-03-31 |  |  | 0 | 5000 | 0
[8 empty] | 0 | 0 |  |  | 0
Presentation CD/DVD Takeaway | [7 empty] | 0 | 0 |  |  | 0
| Revision of general presentation (including approvals) |  |  | 3000 |  | 2007-04-01 | 2007-04-30 | 3000 | 0 |  |  | 300 | 300 | 2007-01-02
| Production: Presentation CD/DVD Takeaway |  | 1000 |  | 2500 | 2007-04-01 | 2007-05-15 | 0 | 2500 |  |  | 0
[8 empty] | 0 | 0 |  |  | 0
General Information Brochure | [7 empty] | 0 | 0 |  |  | 0
| Writing/Editing (including approvals) |  |  | 1500 |  | 2007-03-01 | 2007-04-01 | 1500 | 0 |  |  | 0
| Graphic Design (including approvals) |  |  | 500 |  | 2007-03-01 | 2007-04-01 | 500 | 0 |  |  | 525 | 525 | 2008-02-04
| Printing: General Information Brochure |  | 1000 |  | 1200 |  |  | 0 | 1200 |  |  | 0
[8 empty] | 0 | 0 |  |  | 0
Case Studies/Print Testimonials (PDF Only) | [7 empty] | 0 | 0 |  |  | 0
| Writing/Editing ($1,000/each) (including approvals) |  | 3 | 3000 |  | 2007-02-01 | 2007-03-31 | 3000 | 0 |  |  | 0
| Graphic Design (including approvals) |  |  | 500 |  | 2007-02-01 | 2007-03-31 | 500 | 0 |  |  | 0
[8 empty] | 0 | 0 |  |  | 0
Field Personnel Brochure | [7 empty] | 0 | 0 |  |  | 0
| General brochure revision (including approvals) |  |  | 1000 |  | 2007-05-01 | 2007-06-30 | 1000 | 0 |  |  | 0
| Graphic Design for PDF (including approvals) |  |  | 1000 |  | 2007-05-01 | 2007-06-30 | 1000 | 0 |  |  | 1650 | 1650 | 2008-03-12
| Printing Field Personal Brochure |  | 1000 |  | 1000 | 2007-07-01 | 2007-07-31 | 0 | 1000 |  |  | 0
[8 empty] | 0 | 0 |  |  | 0
MDSS Deployment Guide | [7 empty] | 0 | 0 |  |  | 0
| Writing/Editing (including approvals) |  |  | 5000 |  | 2007-05-01 | 2007-06-30 | 5000 | 0 |  |  | 0
| Graphic Design for PDF (including approvals) |  |  | 500 |  | 2007-05-01 | 2007-06-30 | 500 | 0 |  |  | 0
| Deployment Brochure |  | 500 |  | 3000 | 2007-07-01 | 2007-07-31 | 0 | 3000 |  |  | 0
[8 empty] | 0 | 0 |  |  | 0
Regional Workshop Content | [7 empty] | 0 | 0 |  |  | 0
| Outline of Workshop (including approvals) |  |  | 0 |  | 2007-03-01 | 2007-06-30 | 0 | 0 |  |  | 0
| Presentations |  |  | 0 |  | 2007-03-01 | 2007-06-30 | 0 | 0 |  |  | 0
| Handouts |  |  | 0 |  | 2007-03-01 | 2007-06-30 | 0 | 0 |  |  | 0
| Travel, Hotel and Food for DOT Personnel |  | 50 |  | 40000 | 2007-08-01 | 2007-10-31 |  |  | 0 | 40000 | 0
| Other cost (AV, Conference Room Rental, etc…) |  |  |  | 5000 | 2007-08-01 | 2007-10-31 |  |  | 0 | 5000 | 0
[8 empty] | 0 | 0 |  |  | 0
Press Kit | [7 empty] | 0 | 0 |  |  | 0
| Materials Development (including approvals) |  |  | 1800 |  | 2007-04-01 | 2007-04-30 | 1800 | 0 |  |  | 0
| Printing/Assembly |  |  |  | 500 | 2007-04-01 | 2007-05-15 | 0 | 500 |  |  | 0
[8 empty] | 0 | 0 |  |  | 0
Website | [7 empty] | 0 | 0 |  |  | 0
| Outline/Design (including approvals) |  |  | 500 |  | 2007-02-15 | 2008-02-29 |  |  | 500 | 0 | 0
| Materials Creation (including approvals) |  |  | 2500 |  | 2007-04-15 | 2008-03-31 |  |  | 2500 | 0 | 0
[8 empty] | 0 | 0 |  |  | 0
E-Blast Alerts | [7 empty] | 0 | 0 |  |  | 0
| E-blast announcing web site launch |  | 1 | 0 |  | 2007-06-01 | 2007-06-01 | 0 | 0 |  |  | 0
| E-blast alerts (Blast vendor fee plus 2 hours development) |  | 3 | 300 | 500 | 2007-11-01 | 2008-03-15 |  |  | 300 | 500 | 0
[8 empty] | 0 | 0 |  |  | 0
Marketing Consultant | [7 empty] | 0 | 0 |  |  | 0
| Labor for ongoing support and counsel (hours) |  | 24 | 3600 |  | 2007-02-01 | 2008-03-31 |  |  | 3600 | 0 | 0
0
|  |  | Total | 35000 | 61700 | [6 empty] | 0
[8 empty] | FY 07 | 36300 | FY 08 | 60400 | 2475
|  |  | TOTAL | 96700
[8 empty] | Services | 300
[8 empty] | Consultant | 8909
9209
-27091

## PCPS
Budget Estimate for the AASHTO TIG Lead States Team
Precast Concrete Panels for Pavement
Cost
DESCRIPTION of ACTION ITEMS | Estimate | Actual
1. AASHTO Website - e-Marketing | 0
(assumes AASHTO will be willing to work with TIG in
setting up and adding to existing TIG website)
2. Develop Design Guidance | 0
3. State/Metropolitan Workshops (assume 3 of)
Hotel Conference Room (est. $3,000/ea) | 9000
Audio-Visual Needs (est. $500/ea.) | 1500
2 AASHTO Members Travel ($1000/pp/trip) | 6000
Postage/shipping costs - written/electronic media | 300
Invitations, name tags, misc. mtg. expenses | 600
Report on activities (see below)
4. Personal Letter Campaign
Postage | 200
5. AASHTO Members - LST Presentations
Professionally refine 2 presentations | 5000
- (Assume 20 presentations)
- AASHTO member Travel Expenses ($1500/trip) | 30000
6. Press Release/Trade Journal Article(s) | 0
7. Written documentation - publication/printing
Assume 500 copies - 25 pages each | 5000
500 Folders | 1000
8. Electronic documentation - publication/production
assume 500 - 1000 CDs w/case | 5000
9. Professional Services Contract
Mark B. Snyder - professional recorder
a. 2-day Kick-off Mtg. - Saratoga, NY
25 hrs @ $75/hr (travel, attend mtg, prepare minutes) | 1875
Estimated Travel Expenses | 1300
b. 2-day Team Meeting - Houston, TX
25 hrs @ $75/hr (travel, attend mtg., prepare minutes) | 1875
Estimated Travel Expenses | 1300
c. 1-day Metropolitan Workshop - Location TBD
15 hrs @ $75/hr (travel, attend mtg., prepare report) | 1125
Estimated Travel Expenses | 1300
d. Provide Assistance on final LST Close-out Report
20 hrs @$75/hr (draft, review, final) | 1500
10. Team Meeting - Houston, TX (2-day meeting)
Assume 9 AASHTO Members participate
Travel Expenses for 9 members | 11250
Misc. Meeting Expenses | 1500
11. Professional Communications Service Contract
To provide professional communication services that | 10000
would refine and augment outreach efforts. Provides
Team with Task-order Contract Vehicle to accomplish
goals & objectives.
TOTAL Budget Request | 96625
Travel | 5416
Consultant | 1050
6466
-90159

## SPMT
[7 empty] | Proposed Budget | [6 empty] | Actual Costs
[7 empty] | FY08 |  | FY09 |  | FY10 |  | Subtotals of Costs to AASHTO | FY08 |  | FY09 |  | FY10
Cost Type/Description | Cost | Location (FY08) | Locations (FY09) | Locations (FY10) | Number of team members | Estimated Non-reimbursed Costs to Lead States** | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO |  | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO
Promotional Material
Brochure | [6 empty] | 1000 | 2000 |  |  |  |  | 3000 |  | 575
Website | [12 empty] | 0 |  | 262.5
PPT | [6 empty] | 2000 | [5 empty] | 2000 |  | 2587.5
E-Mail Blast (1) | [8 empty] | 150 | 500 |  |  | 650
Trade Journal Articles (1) | [6 empty] | 3000 | [5 empty] | 3000
Surveys (2) | [12 empty] | 0
Total Promotional Material | [5 empty] | 0 | 6000 | 2000 | 150 | 500 | 0 | 0 | 8650
Operating and Other Expenses | [12 empty] | 0
Travel for Task 1: a) 4 trips for presentations at key meetings/conferences x 1 LST member | 1200 | 1 | 2 | 1 | 1 |  |  | 1200 |  | 2400 |  | 1200 | 4800
b) 10 trips to target States x 2 LST members during project period | 1200 | 3 | 3 | 4 | 2 |  |  | 7200 |  | 7200 |  | 9600
c) 1 LST member to TRB meeting for presentation; plus State agency paid travel for additional representative | 1200 | 1 |  |  | 1 |  |  | 1200 |  | 0 |  | 0
Travel for Task 2: 5 trips x 1 LST members for technical assistance to States | 1200 | 3 | 2 |  | 1 |  |  | 3600 |  | 2400 |  | 0 | 6000
Travel for Task 3: 5 trips x 1 LST members for technical assistance to Local agencies/MPO's/toll facilities | 1200 | 3 | 2 |  | 1 |  |  | 3600 |  | 2400 |  | 0 | 6000
Travel for interim LST team meeting x 5 LST members | 1200 |  | 1 |  | 5 |  |  | 0 |  | 6000 |  | 0 | 6000
Expenses for interim LST team meeting (meeting room rental, food, etc.) | [9 empty] | 2000 |  | 0 | 2000
Expenses for initial LST team meeting | [7 empty] | 10000 |  |  |  |  | 10000
Expense for marketing plan development | [6 empty] | 4500 | [5 empty] | 4500 | 1950 | 600
Expense for ongoing marketing support & counsel | [6 empty] | 3000 |  | 3000 |  | 3000 |  | 9000
LST Conference Calls/E-Communications
Total Operating/Other Expenses | [5 empty] | 0 | 7500 | 26800 | 3000 | 22400 | 3000 | 10800 | 73500
Expendable Goods & Supplies | [12 empty] | 0
Long Distance Telephone Charges | [7 empty] | 250 |  | 250 |  | 250 | 750
Reproduction | [7 empty] | 250 |  | 250 |  | 250 | 750
Shipping | [7 empty] | 250 |  | 250 |  | 250 | 750
Equipment Rental | [7 empty] | 250 |  | 250 |  | 250 | 750
Total Expendable Goods & Supplies | [5 empty] | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 3000
Equipment Purchase
Total Equipment Purchase | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontracts*
Bridge/Structures Consultant (Ralls) | [6 empty] | 2500 |  | 2500 |  | 2500
Total Subcontractors
Total Lead States Contribution | [5 empty] | 0
Total AASHTO Request | [6 empty] | 13500 | 29800 | 3150 | 23900 | 3000 | 11800 | 85150
[7 empty] | FY 08 Total | 43300 | FY 09 Total | 27050 | FY 10 Total | 14800
*Subcontracts should be established directly with AASHTO. Contact the AASHTO TIG Program Manager for assistance.
**Estimated labor and travel costs for 3-year performance period. | [6 empty] | Travel | 6425
Notes: | [6 empty] | Services | 421
1. The proposed AASHTO reimbursed budget is not to include salary and fringe benefits for lead states team members providing services. | [6 empty] | Consultant | 15322
2. Travel expenses for lead states team members reprenting industry are not reimbursable by AASHTO. | [7 empty] | 22168
3. Appropriate indirect charges may be included in the individual cost estimates above. | [7 empty] | -21132

## AMG
[8 empty] | Proposed Budget | [6 empty] | Actual Costs
[8 empty] | FY08 |  | FY09 |  | FY10 |  | Subtotals of Costs to AASHTO | FY08 |  | FY09 |  | FY10
Cost Type/Description | Cost | Locations (FY08) | Locations (FY09) | Locations (FY10) | Number of trips/yr | Number of team members | Estimated Non-reimbursed Costs to Lead States | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO |  | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO
Promotional Material | [15 empty] | 3000
Brochure | [6 empty] | 2750 | 700 | 2000 |  |  |  |  | 2700 |  | 3500
Website | [6 empty] | 2250 | [6 empty] | 0 |  | 1120
PPT | [6 empty] | 3000 | 300 | [5 empty] | 300 | 300 | 2500
E-Mail Blast (1) | [7 empty] | 150 | 500 | 150 | 500 | 150 | 500 | 1950
Trade Journal Articles (1) | [6 empty] | 3225 | 0 | [5 empty] | 0
Surveys (2) | [6 empty] | 27000 | [6 empty] | 0
Total Promotional Material | [6 empty] | 38225 | 1150 | 2500 | 150 | 500 | 150 | 500 | 4950
Operating and Other Expenses | [13 empty] | 0
Travel for Task 1: Visit 6 target States 2x each during project period, plus additional States/trips as needed to meet goal; 2 LST members toTRB meeting for presentation; plus State agency paid travel for additional representatives | 1200 | 4 | 2 | 2 | 2 | 2 | 86400 |  | 19200 |  | 9600 |  | 9600 | 38400 | 4734
Travel for Task 3: 2 workshops/year in FY 08 and 09 (using webinars/electronic media, if possible) | [6 empty] | 12300 |  | 0 |  | 0 |  |  | 0
Travel for Task 4: national/regional meetings for presentations to contractors; plus agency-paid travel for additional representatives | 1200 | 1 | 1 |  | 1 | 1 | 3600 |  | 1200 |  | 1200 |  |  | 2400
Travel for Task 7: national/regional meetings for presentations to agency personnel; plus agency-paid travel for additional representatives | 1200 | 1 | 1 |  | 1 | 1 | 97200 |  | 1200 |  | 1200 |  |  | 2400
Travel for interim LST team meeting, plus agency-paid travel for additional LST members | 1200 |  | 1 |  | 1 | 7 | 34800 |  |  |  | 8400 |  |  | 8400
Expenses for interim LST team meeting (meeting room rental, food, etc.) | [6 empty] | TBD | [6 empty] | 0
Expenses for initial LST team meeting | [6 empty] | 27600 |  | 10000 |  |  |  |  | 10000
Expense for marketing plan development | [7 empty] | 4500 | [5 empty] | 4500 | 1950
Expense for ongoing marketing support & counsel | [6 empty] | 7500 | 3000 |  | 3000 |  | 3000 |  | 9000
Development of inspection technician QA/QC guidance for TIG/AMG website | [6 empty] | 93000 | [6 empty] | 0
Total Operating/Other Expenses | [6 empty] | 362400 | 7500 | 31600 | 3000 | 20400 | 3000 | 9600 | 75100
Expendable Goods & Supplies | [13 empty] | 0
Long Distance Telephone Charges | [6 empty] | TBD |  | 250 |  | 250 |  | 250 | 750
Reproduction | [6 empty] | TBD |  | 250 |  | 250 |  | 250 | 750 |  | 929.88
Shipping | [8 empty] | 250 |  | 250 |  | 250 | 750
Equipment Rental | [6 empty] | TBD |  | 250 |  | 250 |  | 250 | 750
Total Expendable Goods & Supplies | [6 empty] | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 3000
Equipment Purchase
TBD | [6 empty] | TBD
Total Equipment Purchase | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontracts*
TBD
Total Subcontractors
Total Lead States Contribution | [6 empty] | 400625
Total AASHTO Request | [7 empty] | 8650 | 35100 | 3150 | 21900 | 3150 | 11100 | 83050 | 6984 | 11049.88 | 0 | 0
[8 empty] | FY 08 Total | 43750 | FY 09 Total | 25050 | FY 10 Total | 14250
*Subcontracts should be established directly with AASHTO. Contact the AASHTO TIG Program Manager for assistance.
[8 empty] | Travel | 6984 | Travel
Notes: | [7 empty] | Consultant | 11051 | Consultant
1. The proposed AASHTO reimbursed budget is not to include salary and fringe benefits for lead states team members providing services. | [8 empty] | 18035
2. Travel expenses for lead states team members reprenting industry are not reimbursable by AASHTO. | [8 empty] | -25715 |  | -25050
3. Appropriate indirect charges may be included in the individual cost estimates above.

## LRS
| FY09 | FY10 | FY11 | Total
Budgeted | 27500 | 28500 | 19000 | 75000
Spent | 2768.29 | 2577 |  | 5345.29

## SR
| FY09 | FY10 | FY11 | Total
Budgeted | 60900 | 5400 | 23350 | 89650
Spent | 43425.44 | 779 |  | 44204.44

## UREDMS
| FY10 | FY11 | FY12 | Total
Budgeted |  | 21200 | 16900 | 38100
Spent | -8388 |  |  | -8388

## GCEDMS
| FY10 | FY11 | FY12 | Total
Budgeted | 9450 | 14850 | 17550 | 41850
Spent | 3064 |  |  | 3064

## EPGT
| FY10 | FY11 | FY12 | Total
Budgeted | 6500 | 14000 | 17400 | 37900
Spent | 5083 |  |  | 5083

## TowPlow
| FY11 | FY12 | Total
Budgeted | 26500 | 11600 | 38100
Spent |  |  | 0

## 2006 AST
2006 AST Budget
|  |  |  | Proposed Budget | Actual Spent | Date Updated
AST Fact Sheet #1: Slope Stabilization Using Recycled Plastic Reinforcement
- Interviews with AST principal(s) |  | 3 Hours
- Research |  | 3 Hours
- Content Planning |  | 1 Hour
- Writing and Editing |  | 8 Hours
Subtotal | 15 Hours at $150/Hour |  |  | 2250 | 1950 | 2007-09-24 | 37.5 | 2007-11-09 |  |  |  |  | 1987.5
AST Fact Sheet #2: Embedded Data Collector
- Interviews with AST principal(s) |  | 3 Hours
- Research |  | 3 Hours
- Content Planning |  | 1 Hour
- Writing and Editing |  | 8 Hours
Subtotal | 15 Hours at $150/Hour |  |  | 2250 | 1950 | 2007-09-24 | 450 | 2007-11-09 |  |  | 150 | 2008-02-04 | 2550
AST Fact Sheet #3: Low Profile Barrier System
- Interviews with AST principal(s) |  | 3 Hours
- Research |  | 3 Hours
- Content Planning |  | 1 Hour
- Writing and Editing |  | 8 Hours
Subtotal | 15 Hours at $150/Hour |  |  | 2250 | 0 |  | 1200 | 2007-11-09 | 450 | 2008-03-12 |  |  | 1650
Design/Graphics (All Three ASTs)
- Artwork
- Layout
- PDF Preparation
- Web Design and Formatting (including appropriate links)
Subtotal | 8 Hours at $150/Hour |  |  | 1200 |  |  |  |  | 525 | 2007-12-20 | 75 | 2008-04-04 | 600
|  |  | TOTAL: | 7950 | 3900 |  | 5587.5 |  | 6562.5 |  | 6787.5
|  |  | Amount Left | 1162.5 |  | 2007-09-24 |  | 2007-11-09 |  | 2007-12-20 |  | 2008-02-04

## CAST
Budget for CAST Marketing Plan
Activity |  |  | Lead | Time Frame | Due Date | Fiscal | Funding Needs |  | FY
[6 empty] | Year | AASHTO | FHWA | 2007 | 2008 | Actual Spent | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date | Amount | Invoice Date
Development | a) Brochure (Product information – AASHTO) (Product Evaluation – FHWA) |  | Platte |  | Draft – Feb 22 Finalized - April 2007 | 2007 | 20,000 (Worth) | 0 | 20,000 (Worth) |  | 6375 | 1537.5 |  | 1800 | 2007-11-09 | 1462.5 | 2007-12-20 | 150 | 2008-01-03 | 975 | 2008-02-04 | 450 | 2008-03-12
| b) Presentation materials | High Level, Decision Makers (30 min) | Samadian |  | June 07 | 2007 | 1000 |  | 1000
|  | Detail Level, End Users | Velado |  | June 07 | 2007 | 2000 |  | 2000
| c) Case Studies (Identify States with experience) (CA, WA, Utah, Minnesota, Iowa, Alabama, others) |  | EB Lee |  | 2 per Quarter |  | 12000 |  | 4000 | 8000
(Worth)
| d) Video (Based on High Level Presentation) |  | Platte/ Samadian |  | Jan 07 | 2007 | 3000 |  | 3000
| e)Pilot Regional workshop (First come, first serve in an “experienced” state or in an “interested” state) |  | Samadian/ Farnbach |  | Mar 07- July 07 | 2008 | 15000 |  |  | 15000
Delivery | a) September 2006 Kick-off |  | Caltrans | Done | Sept 06 | 2007 | 10000 |  | 10000
| b) October 2006 AASHTO Annual Meeting |  | Caltrans | Done | Oct 06 | 2007 | None |  | None
| c) December 2006 Reassembly Meeting |  | Caltrans | Done | Dec 06 | 2007 | 3000 |  | 3000
| d) WASTO-X Meeting (CD of presentation is available) |  | Dietz | Done | Dec 06 | 2007 | 0 |  | 0
| e) Video Production and distribution |  | CAST Team |  | Feb 07 - April 07 | 2007 | 7000 |  | 7000
| f) Printing & Sending brochures & Case Studies |  | Platte |  | April 07 - May 07 | 2007 | 5000 |  | 5000
| g) Presentations Location (SCOD, SCOC, SCOTE, WASHTO 2007) |  | Samadian |  | June 07 - Aug 07 | 2007-8 | 5000 |  | 4000 | 1000
| h)Mid Project Team Meeting |  | Platte/ CAST Team |  | June 07 | 2007 | 5000 |  | 5000
| i) Pilot Regional workshop (only one) |  | Samadian |  | Sept 07 | 2008 | 15000 |  |  | 15000
| j) Software Demonstration and Technical Support (Upon request of state) (Limited to 4-6) |  | Samadian |  | 2-4/year (Nov 07 -Jun 08) | 2008 | 10000 | 30000 |  | 10000
| k) Conduct Close out Survey and Produce Closeout Report |  | Samadian / Platte |  | June 08 | 2008 | 1000 |  |  | 1000
[6 empty] | FY 07 | 44000
[6 empty] | FY 08 | 50000 | 30000
[6 empty] | Total | 94000 | 30000 | 44000 | 50000 | 6375
[8 empty] | Services | 300
[8 empty] | Consultant | 8775
9075
-34925

## WIM
Activity | Budget |  |  | Project Schedule
| Original Proposed Activity & Estimated Cost | Revised Proposed Activity & Estimated Cost | Actual Cost | Projected Start Date | Projected End Date | Actual End Date
Project Development & Data Gathering
Organizational Meeting for Technical Panel (work plan & budget development) | 4000 |  | 4000 | 2005-08-23 | 2005-08-24
Submission of Work Plan & Budget to AASHTO - TIG |  |  |  | 2005-09-12 | 2005-10-01
Conduct Survey for “Best Practices” | 0 |  | 0 | 2005-10-01 | 2005-10-22
FHWA European Scan Tour |  |  | 4000
Subtotal | 4000 |  | 8000
Promotional Message Development
Develop Powerpoint Presentation (includes printing and CD costs) | 3000 |  |  | 2005-10-01 | 2006-02-01
40+ slide version of PP (contracted = 20 hrs., actual = 93.5 hrs.) |  | 3000 | 3000
40+ slide version of PP - plus narration (contracted = xx hrs., actual = xx hrs.) |  | 7795.26 | 1000
15+ slide version of PP (contracted = xx hrs., actual = xx hrs.) |  | 4045.26 | 4045
Develop Video (Worth Assoc. est. 10 min.= $10,500) | 15000 | Cancelled
Develop Brochure (Worth Associates) | 5000 | 2850 | 2850 | 2005-10-01 | 2006-11-01
Design, Layout, Typeset (Piedmont = 4hrs + Worth Assoc. = 1hr ($150.hr)) |  |  | 750 |  | 2006-11-01
Printing - Piedmont (per 5,000 copies) |  |  | 1468.35 |  | 2006-11-01
Subtotal | 23000 |  | 13113.35
Project Evaluation Meetings
Mid-Point Project Evaluation Meeting | 5000 | Cancelled | 0 | 2006-02-01
Final Project Evaluation Meeting | 6000 |  |  | 2007-09-05 | 2007-09-06
Subtotal | 11000 |  | 0
Message Delivery
Delivery of Promotional Message | 12000 |  |  | 2006-02-03 | 2007-09-01
Project Completion & Final Results to AASHTO-TIG |  |  |  |  | 2007-10-01
Subtotal | 12000 |  | 0
Total | 50000 |  | 21113.35
Budget Remaining |  |  | 28886.65 |  | Revision | 2007-03-13
18000
10886.65

## RSA
Implementation Budget and Projected Time Schedule (8/31/07 update)
Activity | Activity | Activity | Projected | Projected
| Projected | Actual | Start Date | End Date
| Cost | Costs |  |  | Notes
Organizational Meetings
o Kick Off TRB 1/11/05 |  |  | 2005-01-11 | 2005-01-11
o Teleconference 10/25/05 |  |  | 2005-10-25 | 2005-10-25
o TRB 1/23/06 |  |  | 2006-01-23 | 2006-01-23
o Spring/Summer 2006 (teleconference) |  |  |  | NA
o Fall/Winter 2006 (Washington DC) | 6000 | 6000 |  | Done
o TRB 2007 |  |  |  | Done
Submission of Work Plan & Budget for |  |  | 2006-02-21 | 2006-02-22
AASHTO TIG approval |  |  |  | Done
Conduct Survey of State Safety Directors
o Determine status and interest | Done
o Feedback on implementation |  |  | 2007 | 2007
Conduct Survey of Local Gov't Agencies
o Determine use and interest |  |  | 2006 | 2006
o Gain feedback on implementation |  |  | 2007 | 2007
Develop & Implement Promotional Matls
& Message
o FHWA DA Briefings
o Position Paper on Liability Concerns
o Develop & Distribute RSA Video | HSA+HfL |  | Spring 06 | Fall 06 | Believe Done
- Load on appropriate websites |  |  | Spring 06 | Done
o National Association Presence/brief | 10000 |  | 2006 | 2007 | Done
o RSA presentations statewide/regional | 10000 |  | 2006 | 2007 | Ongoing
o Regional LRC Meetings (4 in 2 years) | 6000 |  | 2008 | 2009 | Ongoing
Conduct Peer Reviews
o National Peer Review (state oriented) | 40000 | 15000 | 2007 | 2007 | Co-sponsor with HfL ($35,000)
o Regional Peer Reviews - 4 (state/local) | 27000 |  | 2007 | 2008 | Co-sponsor with HfL ($33,000)
(2 in 2008; 2 in 2009) |  |  |  |  | (Use $52,000 Avail from est.)
Develop Training Materials
o Develop NHI Training Materials | Done |  | 2003 | 2003
o Develop LTAP/TTAP Training Matl. | Done |  | 2005 | 2005
o Update NHI Trng Materials | HfL funds
Mid Point Evaluation - TRB 2007 |  | 1541.58 | 2007-01-01
Final Evaluation - TRB 2008 |  |  | 2008-01-01
Final Results |  |  | 2008-09-08
Total Cost of Program | 99000 | 22541.58
Note: HfL - Highways for Life
LRC-Local Road Coordinators

## CMB
Proposed Work Plan |  |  |  |  | Proposed Budget | Actual Spent | Amount | Date of Invoice | Amount | Date of Invoice
· Meetings to Discuss Production of Materials for CMBBPG – | [5 empty] | 0
0
| Assume 2 meetings for travel and lodging: |  |  |  |  | 0
|  | 8 out of state participants @ $1,500 each |  |  | 24000 | 0
|  | 6 in state participants @ $200 each |  |  | 2400 | 0
0
0
· Production of Marketing and Technical Materials for CMBBPG – | [5 empty] | 0
0
Task 1 | Brochures* - 500 color – Brochure will discuss a basic overview of the TIG-Cable Median Barrier Initiative and the Production of Videos and Information Modules for CMBBPG. |  |  |  |  | 0
|  | Development |  |  | 1000 | 187.05 | 187.05
|  | Printing ($2.00 ea. estimated) |  |  | 1000 | 0
0
Task 2 | Video* for Media/Public (in DVD or .mpeg format) – Video will be approximately 15-20 minutes in length and target a Non-Technical audience with a basic overview of the TIG-Cable Median Barrier Initiative and the Information Modules for CMBBPG. |  |  |  |  | 0
|  |  | Develop script |  | 3000 | 0
|  |  | Edit footage |  | 3000 | 0
|  |  | Narrator and sound studio |  | 3000 | 0
|  |  | Distribution |  | 1000 | 0
0
Task 3 | Video* for States (in DVD or .mpeg format) – Video will be approximately 15-20 minutes in length and target a Technical audience with a basic overview of the TIG-Cable Median Barrier Initiative and the Information Modules for CMBBPG. |  |  |  |  | 0
|  |  | Develop script |  | 3000 | 0
|  |  | Edit footage |  | 3000 | 0
|  |  | Narrator and sound studio |  | 3000 | 0
|  |  | Distribution |  | 1000 | 0
0
Task 4 | Information Modules* to address the five (5) Emphasis Areas established by the TIG-Cable Median Barrier Initiative Workgroup. These Modules will consist of a Presentation of Lead State Cable Median Barrier Technical Issues and Experiences for each Emphas |  |  |  |  | 0
0
|  | Background and Problem Identification |  |  | 5000 | 0
|  | Roadway Design Issues |  |  | 5000 | 0
|  | Maintenance Issues |  |  | 5000 | 0
|  | Benefits and Evaluation |  |  | 5000 | 0
|  | System Threats |  |  | 5000 | 0
0
| * Note: The goal is to have all information above produced in electronic formatting (.mpeg, .ppt, .pdf, .dgn, .xls, .doc, .jpg, .tiff, etc) to be burned on a Compact Disc (CD) for mass distribution. |  |  |  |  | 0
0
· Presentations at National Conventions by Workgroup Members – | [5 empty] | 0
| Assume 8 conferences for travel and lodging: |  |  |  |  | 0
|  | 2 participants per conference @ $1,500 each |  |  | 24000 | 0
|  |  |  | Total Proposed Budget | 97400 | 187.05