## TIG Summary
TIG Program Reserve as of September 14th, 2007
628816
Status | Year | Focus Technologies | Initial Approved Budget |  | Revised Budget | Spent in FY 2004 (July 03-July 04) | Spent in FY 2005 (July 04-July 05) | Spent in FY 2006 (July 05-July 06) | Spent in FY 2007 (July 06-July 07) | Spent in FY 2008 (July 07-August 07) | Current Remaining Budget | Projected Costs in FY 2008 | Total Cost in FY 2008 (Projected + Spent) | Focus Technology $ Programed beyond FY 08 | Returned funds in 2007 | Additional Info
Active | 2004 | RSA | 167000 |  | 99000 |  |  | -232 | -17731 | 0 | 81037 | -50000 | -50000 | 31037 | 0 | In progress…
Active | 2004 | WIM | 50000 |  |  |  |  | -12986 | -16184 | 0 | 20830 | -20830 | -20830 | 0 | 0 | In progress…
Active | 2004 | CMB | 97400 |  |  |  |  | -1029 | -12105 | -2605 | 81661 | -15000 | -17605 | 66661 | 0 | In progress…
Active | 2005 | CAST | 94000 | [5 empty] | -8332 | -2100 | 83568 | -47900 | -50000 | 35668 | 0 | In progress…
Active | 2005 | MDSS | 96700 | [5 empty] | -12341 | -600 | 83759 | -59800 | -60400 | 23959 | 0 | In progress…
Active | 2005 | PCPS | 96625 | [5 empty] | -7042 |  | 89583 | -50000 | -50000 | 39583 | 0 | In progress…
Active | 2006 | SPMT's | 85150 | [5 empty] | 0 | -8607 | 76543 | -43300 | -51907 | 33243 |  | In progress…
Active | 2006 | AMG | 83050 | [5 empty] | 0 | -11643 | 71407 | -43750 | -55393 | 27657 |  | In progress…
| 2007 |  | 10000 | s |  |  |  |  | 0 |  | 10000 | -10000 |  | 0
| 2007 |  | 10000 | s |  |  |  |  | 0 |  | 10000 | -10000
| 2007 |  | 10000 | s |  |  |  |  | 0 |  | 10000 | -10000
Active | 2006 | AST (non-focus tech) | 7950 | [5 empty] | 0 | -150 | 7800 | -7800 | -7950 | 0
| 2007 | AST (non-focus tech) | [8 empty] | 0
|  | TIG Gen (Other Outside Support) | 20000 | [5 empty] | -21034 | -1038 | -2072 | -10000 | -11038 |  | 0
|  | Staff(Overhead & Benefits) | [6 empty] | -48926 | -43231 |  | -45000 | -88231 |  | 0
[9 empty] | -143695 | -69974 | 440438 | -423380 | -463354 | 257808 | 0
[9 empty] | Program Reserve at FY 07: | 496816
|  | Additions | [6 empty] | Collected Funds (FY 08): | 132000
|  | Current Program Money Total | 628816 | [5 empty] | FY 07 Expenses: | -143695
|  | Estimated Total FY 08: | -463354 | [5 empty] | (YTD) FY 08 Expenses: | -69974
|  | Estimated Reserve EOY 2008 | 165462 | [5 empty] | Current Program Money Total: | 628816
Deductions
|  | Focus Techs' $ Programed | 257808
|  | Sum Deductions: | 257808
|  | Est Reserve After FY 2008 | -92346

## CMB
Proposed Work Plan |  |  |  |  | Proposed Budget | Actual Spent
· Meetings to Discuss Production of Materials for CMBBPG –
Assume 2 meetings for travel and lodging:
|  | 8 out of state participants @ $1,500 each |  |  | 24000
|  | 6 in state participants @ $200 each |  |  | 2400
· Production of Marketing and Technical Materials for CMBBPG –
Task 1 | Brochures* - 500 color – Brochure will discuss a basic overview of the TIG-Cable Median Barrier Initiative and the Production of Videos and Information Modules for CMBBPG.
|  | Development |  |  | 1000
|  | Printing ($2.00 ea. estimated) |  |  | 1000
Task 2 | Video* for Media/Public (in DVD or .mpeg format) – Video will be approximately 15-20 minutes in length and target a Non-Technical audience with a basic overview of the TIG-Cable Median Barrier Initiative and the Information Modules for CMBBPG.
|  |  | Develop script |  | 3000
|  |  | Edit footage |  | 3000
|  |  | Narrator and sound studio |  | 3000
|  |  | Distribution |  | 1000
Task 3 | Video* for States (in DVD or .mpeg format) – Video will be approximately 15-20 minutes in length and target a Technical audience with a basic overview of the TIG-Cable Median Barrier Initiative and the Information Modules for CMBBPG.
|  |  | Develop script |  | 3000
|  |  | Edit footage |  | 3000
|  |  | Narrator and sound studio |  | 3000
|  |  | Distribution |  | 1000
Task 4 | Information Modules* to address the five (5) Emphasis Areas established by the TIG-Cable Median Barrier Initiative Workgroup. These Modules will consist of a Presentation of Lead State Cable Median Barrier Technical Issues and Experiences for each Emphas
|  | Background and Problem Identification |  |  | 5000
|  | Roadway Design Issues |  |  | 5000
|  | Maintenance Issues |  |  | 5000
|  | Benefits and Evaluation |  |  | 5000
|  | System Threats |  |  | 5000
* Note: The goal is to have all information above produced in electronic formatting (.mpeg, .ppt, .pdf, .dgn, .xls, .doc, .jpg, .tiff, etc) to be burned on a Compact Disc (CD) for mass distribution.
· Presentations at National Conventions by Workgroup Members –
Assume 8 conferences for travel and lodging:
|  | 2 participants per conference @ $1,500 each |  |  | 24000
|  |  |  | Total Proposed Budget | 97400

## RSA
Implementation Budget and Projected Time Schedule (8/31/07 update)
Activity | Activity | Activity | Projected | Projected
| Projected | Actual | Start Date | End Date
| Cost | Costs |  |  | Notes
Organizational Meetings
o Kick Off TRB 1/11/05 |  |  | 2005-01-11 | 2005-01-11
o Teleconference 10/25/05 |  |  | 2005-10-25 | 2005-10-25
o TRB 1/23/06 |  |  | 2006-01-23 | 2006-01-23
o Spring/Summer 2006 (teleconference) |  |  |  | NA
o Fall/Winter 2006 (Washington DC) | 6000 | 6000 |  | Done
o TRB 2007 |  |  |  | Done
Submission of Work Plan & Budget for |  |  | 2006-02-21 | 2006-02-22
AASHTO TIG approval |  |  |  | Done
Conduct Survey of State Safety Directors
o Determine status and interest | Done
o Feedback on implementation |  |  | 2007 | 2007
Conduct Survey of Local Gov't Agencies
o Determine use and interest |  |  | 2006 | 2006
o Gain feedback on implementation |  |  | 2007 | 2007
Develop & Implement Promotional Matls
& Message
o FHWA DA Briefings
o Position Paper on Liability Concerns
o Develop & Distribute RSA Video | HSA+HfL |  | Spring 06 | Fall 06 | Believe Done
- Load on appropriate websites |  |  | Spring 06 | Done
o National Association Presence/brief | 10000 |  | 2006 | 2007 | Done
o RSA presentations statewide/regional | 10000 |  | 2006 | 2007 | Ongoing
o Regional LRC Meetings (4 in 2 years) | 6000 |  | 2008 | 2009 | Ongoing
Conduct Peer Reviews
o National Peer Review (state oriented) | 40000 | 15000 | 2007 | 2007 | Co-sponsor with HfL ($35,000)
o Regional Peer Reviews - 4 (state/local) | 27000 |  | 2007 | 2008 | Co-sponsor with HfL ($33,000)
(2 in 2008; 2 in 2009) |  |  |  |  | (Use $52,000 Avail from est.)
Develop Training Materials
o Develop NHI Training Materials | Done |  | 2003 | 2003
o Develop LTAP/TTAP Training Matl. | Done |  | 2005 | 2005
o Update NHI Trng Materials | HfL funds
Mid Point Evaluation - TRB 2007 |  | 1541.58 | 2007-01-01
Final Evaluation - TRB 2008 |  |  | 2008-01-01
Final Results |  |  | 2008-09-08
Total Cost of Program | 99000 | 22541.58
Note: HfL - Highways for Life
LRC-Local Road Coordinators

## WIM
Activity | Budget |  |  | Project Schedule
| Original Proposed Activity & Estimated Cost | Revised Proposed Activity & Estimated Cost | Actual Cost | Projected Start Date | Projected End Date | Actual End Date
Project Development & Data Gathering
Organizational Meeting for Technical Panel (work plan & budget development) | 4000 |  | 4000 | 2005-08-23 | 2005-08-24
Submission of Work Plan & Budget to AASHTO - TIG |  |  |  | 2005-09-12 | 2005-10-01
Conduct Survey for “Best Practices” | 0 |  | 0 | 2005-10-01 | 2005-10-22
FHWA European Scan Tour |  |  | 4000
Subtotal | 4000 |  | 8000
Promotional Message Development
Develop Powerpoint Presentation (includes printing and CD costs) | 3000 |  |  | 2005-10-01 | 2006-02-01
40+ slide version of PP (contracted = 20 hrs., actual = 93.5 hrs.) |  | 3000 | 3000
40+ slide version of PP - plus narration (contracted = xx hrs., actual = xx hrs.) |  | 7795.26 | 1000
15+ slide version of PP (contracted = xx hrs., actual = xx hrs.) |  | 4045.26 | 4045
Develop Video (Worth Assoc. est. 10 min.= $10,500) | 15000 | Cancelled
Develop Brochure (Worth Associates) | 5000 | 2850 | 2850 | 2005-10-01 | 2006-11-01
Design, Layout, Typeset (Piedmont = 4hrs + Worth Assoc. = 1hr ($150.hr)) |  |  | 750 |  | 2006-11-01
Printing - Piedmont (per 5,000 copies) |  |  | 1468.35 |  | 2006-11-01
Subtotal | 23000 |  | 13113.35
Project Evaluation Meetings
Mid-Point Project Evaluation Meeting | 5000 | Cancelled | 0 | 2006-02-01
Final Project Evaluation Meeting | 6000 |  |  | 2007-09-05 | 2007-09-06
Subtotal | 11000 |  | 0
Message Delivery
Delivery of Promotional Message | 12000 |  |  | 2006-02-03 | 2007-09-01
Project Completion & Final Results to AASHTO-TIG |  |  |  |  | 2007-10-01
Subtotal | 12000 |  | 0
Total | 50000 |  | 21113.35
Budget Remaining |  |  | 28886.65 |  | Revision | 2007-03-13
18000
10886.65

## MDSS
MDSS Budget | [7 empty] | 2007-09-01
|  |  |  | Development | Delivery |  |  | Development | Delivery | Development | Delivery
Tasks |  |  | Number | Cost | Cost | Start | End | 2007 | 2007 | 2008 | 2008
Enhanced PowerPoint Presentation | [5 empty] | 2007-02-01 | 2007-04-30 | 0 | 0
| Writing/Editing (including approvals) |  |  | 8000 |  | 2007-02-01 | 2007-03-31 | 8000 | 0
| Graphic Design (including approvals) |  |  | 2000 |  | 2007-02-01 | 2007-04-30 | 2000 | 0
| Talking Points Writing/Editing |  |  | 300 |  | 2007-02-01 | 2007-04-30 | 300 | 0
| Meetings/Events | [6 empty] | 0 | 0
|  | Team member travel (1 Person @ $1000 per presentation) | 3 |  | 3000 | 2007-06-01 | 2008-03-31 |  |  | 0 | 3000
| FHWA MDSS RoadShow | [6 empty] | 0 | 0
|  | Team member travel (1 person @ $1000 per meeting) | 5 |  | 5000 | 2007-03-01 | 2008-03-31 |  |  | 0 | 5000
[8 empty] | 0 | 0
Presentation CD/DVD Takeaway | [7 empty] | 0 | 0
| Revision of general presentation (including approvals) |  |  | 3000 |  | 2007-04-01 | 2007-04-30 | 3000 | 0
| Production: Presentation CD/DVD Takeaway |  | 1000 |  | 2500 | 2007-04-01 | 2007-05-15 | 0 | 2500
[8 empty] | 0 | 0
General Information Brochure | [7 empty] | 0 | 0
| Writing/Editing (including approvals) |  |  | 1500 |  | 2007-03-01 | 2007-04-01 | 1500 | 0
| Graphic Design (including approvals) |  |  | 500 |  | 2007-03-01 | 2007-04-01 | 500 | 0
| Printing: General Information Brochure |  | 1000 |  | 1200 |  |  | 0 | 1200
[8 empty] | 0 | 0
Case Studies/Print Testimonials (PDF Only) | [7 empty] | 0 | 0
| Writing/Editing ($1,000/each) (including approvals) |  | 3 | 3000 |  | 2007-02-01 | 2007-03-31 | 3000 | 0
| Graphic Design (including approvals) |  |  | 500 |  | 2007-02-01 | 2007-03-31 | 500 | 0
[8 empty] | 0 | 0
Field Personnel Brochure | [7 empty] | 0 | 0
| General brochure revision (including approvals) |  |  | 1000 |  | 2007-05-01 | 2007-06-30 | 1000 | 0
| Graphic Design for PDF (including approvals) |  |  | 1000 |  | 2007-05-01 | 2007-06-30 | 1000 | 0
| Printing Field Personal Brochure |  | 1000 |  | 1000 | 2007-07-01 | 2007-07-31 | 0 | 1000
[8 empty] | 0 | 0
MDSS Deployment Guide | [7 empty] | 0 | 0
| Writing/Editing (including approvals) |  |  | 5000 |  | 2007-05-01 | 2007-06-30 | 5000 | 0
| Graphic Design for PDF (including approvals) |  |  | 500 |  | 2007-05-01 | 2007-06-30 | 500 | 0
| Deployment Brochure |  | 500 |  | 3000 | 2007-07-01 | 2007-07-31 | 0 | 3000
[8 empty] | 0 | 0
Regional Workshop Content | [7 empty] | 0 | 0
| Outline of Workshop (including approvals) |  |  | 0 |  | 2007-03-01 | 2007-06-30 | 0 | 0
| Presentations |  |  | 0 |  | 2007-03-01 | 2007-06-30 | 0 | 0
| Handouts |  |  | 0 |  | 2007-03-01 | 2007-06-30 | 0 | 0
| Travel, Hotel and Food for DOT Personnel |  | 50 |  | 40000 | 2007-08-01 | 2007-10-31 |  |  | 0 | 40000
| Other cost (AV, Conference Room Rental, etc…) |  |  |  | 5000 | 2007-08-01 | 2007-10-31 |  |  | 0 | 5000
[8 empty] | 0 | 0
Press Kit | [7 empty] | 0 | 0
| Materials Development (including approvals) |  |  | 1800 |  | 2007-04-01 | 2007-04-30 | 1800 | 0
| Printing/Assembly |  |  |  | 500 | 2007-04-01 | 2007-05-15 | 0 | 500
[8 empty] | 0 | 0
Website | [7 empty] | 0 | 0
| Outline/Design (including approvals) |  |  | 500 |  | 2007-02-15 | 2008-02-29 |  |  | 500 | 0
| Materials Creation (including approvals) |  |  | 2500 |  | 2007-04-15 | 2008-03-31 |  |  | 2500 | 0
[8 empty] | 0 | 0
E-Blast Alerts | [7 empty] | 0 | 0
| E-blast announcing web site launch |  | 1 | 0 |  | 2007-06-01 | 2007-06-01 | 0 | 0
| E-blast alerts (Blast vendor fee plus 2 hours development) |  | 3 | 300 | 500 | 2007-11-01 | 2008-03-15 |  |  | 300 | 500
[8 empty] | 0 | 0
Marketing Consultant | [7 empty] | 0 | 0
| Labor for ongoing support and counsel (hours) |  | 24 | 3600 |  | 2007-02-01 | 2008-03-31 |  |  | 3600 | 0
|  |  | Total | 35000 | 61700
[8 empty] | FY 07 | 36300 | FY 08 | 60400
|  |  | TOTAL | 96700

## CAST
Budget for CAST Marketing Plan
Activity |  |  | Lead | Time Frame | Due Date | Fiscal | Funding Needs |  | FY
[6 empty] | Year | AASHTO | FHWA | 2007 | 2008 | Actual Spent
Development | a) Brochure (Product information – AASHTO) (Product Evaluation – FHWA) |  | Platte |  | Draft – Feb 22 Finalized - April 2007 | 2007 | 20,000 (Worth) | 0 | 20,000 (Worth)
| b) Presentation materials | High Level, Decision Makers (30 min) | Samadian |  | June 07 | 2007 | 1000 |  | 1000
|  | Detail Level, End Users | Velado |  | June 07 | 2007 | 2000 |  | 2000
| c) Case Studies (Identify States with experience) (CA, WA, Utah, Minnesota, Iowa, Alabama, others) |  | EB Lee |  | 2 per Quarter |  | 12000 |  | 4000 | 8000
(Worth)
| d) Video (Based on High Level Presentation) |  | Platte/ Samadian |  | Jan 07 | 2007 | 3000 |  | 3000
| e)Pilot Regional workshop (First come, first serve in an “experienced” state or in an “interested” state) |  | Samadian/ Farnbach |  | Mar 07- July 07 | 2008 | 15000 |  |  | 15000
Delivery | a) September 2006 Kick-off |  | Caltrans | Done | Sept 06 | 2007 | 10000 |  | 10000
| b) October 2006 AASHTO Annual Meeting |  | Caltrans | Done | Oct 06 | 2007 | None |  | None
| c) December 2006 Reassembly Meeting |  | Caltrans | Done | Dec 06 | 2007 | 3000 |  | 3000
| d) WASTO-X Meeting (CD of presentation is available) |  | Dietz | Done | Dec 06 | 2007 | 0 |  | 0
| e) Video Production and distribution |  | CAST Team |  | Feb 07 - April 07 | 2007 | 7000 |  | 7000
| f) Printing & Sending brochures & Case Studies |  | Platte |  | April 07 - May 07 | 2007 | 5000 |  | 5000
| g) Presentations Location (SCOD, SCOC, SCOTE, WASHTO 2007) |  | Samadian |  | June 07 - Aug 07 | 2007-8 | 5000 |  | 4000 | 1000
| h)Mid Project Team Meeting |  | Platte/ CAST Team |  | June 07 | 2007 | 5000 |  | 5000
| i) Pilot Regional workshop (only one) |  | Samadian |  | Sept 07 | 2008 | 15000 |  |  | 15000
| j) Software Demonstration and Technical Support (Upon request of state) (Limited to 4-6) |  | Samadian |  | 2-4/year (Nov 07 -Jun 08) | 2008 | 10000 | 30000 |  | 10000
| k) Conduct Close out Survey and Produce Closeout Report |  | Samadian / Platte |  | June 08 | 2008 | 1000 |  |  | 1000
[6 empty] | FY 07 | 44000
[6 empty] | FY 08 | 50000 | 30000
[6 empty] | Total | 94000 | 30000
23500
[10 empty] | 235 |  | 8
[9 empty] | 150 |  |  | 15
[9 empty] | 100 | 15000 |  | 120 | 18000

## PCPS
Budget Estimate for the AASHTO TIG Lead States Team
Precast Concrete Panels for Pavement
Cost
DESCRIPTION of ACTION ITEMS | Estimate | Actual
1. AASHTO Website - e-Marketing | 0
(assumes AASHTO will be willing to work with TIG in
setting up and adding to existing TIG website)
2. Develop Design Guidance | 0
3. State/Metropolitan Workshops (assume 3 of)
Hotel Conference Room (est. $3,000/ea) | 9000
Audio-Visual Needs (est. $500/ea.) | 1500
2 AASHTO Members Travel ($1000/pp/trip) | 6000
Postage/shipping costs - written/electronic media | 300
Invitations, name tags, misc. mtg. expenses | 600
Report on activities (see below)
4. Personal Letter Campaign
Postage | 200
5. AASHTO Members - LST Presentations
Professionally refine 2 presentations | 5000
- (Assume 20 presentations)
- AASHTO member Travel Expenses ($1500/trip) | 30000
6. Press Release/Trade Journal Article(s) | 0
7. Written documentation - publication/printing
Assume 500 copies - 25 pages each | 5000
500 Folders | 1000
8. Electronic documentation - publication/production
assume 500 - 1000 CDs w/case | 5000
9. Professional Services Contract
Mark B. Snyder - professional recorder
a. 2-day Kick-off Mtg. - Saratoga, NY
25 hrs @ $75/hr (travel, attend mtg, prepare minutes) | 1875
Estimated Travel Expenses | 1300
b. 2-day Team Meeting - Houston, TX
25 hrs @ $75/hr (travel, attend mtg., prepare minutes) | 1875
Estimated Travel Expenses | 1300
c. 1-day Metropolitan Workshop - Location TBD
15 hrs @ $75/hr (travel, attend mtg., prepare report) | 1125
Estimated Travel Expenses | 1300
d. Provide Assistance on final LST Close-out Report
20 hrs @$75/hr (draft, review, final) | 1500
10. Team Meeting - Houston, TX (2-day meeting)
Assume 9 AASHTO Members participate
Travel Expenses for 9 members | 11250
Misc. Meeting Expenses | 1500
11. Professional Communications Service Contract
To provide professional communication services that | 10000
would refine and augment outreach efforts. Provides
Team with Task-order Contract Vehicle to accomplish
goals & objectives.
TOTAL Budget Request | 96625

## 2006 AST
2006 AST Budget
|  |  |  | Proposed Budget | Actual Spent
AST Fact Sheet #1: Slope Stabilization Using Recycled Plastic Reinforcement
- Interviews with AST principal(s) |  | 3 Hours
- Research |  | 3 Hours
- Content Planning |  | 1 Hour
- Writing and Editing |  | 8 Hours
Subtotal | 15 Hours at $150/Hour |  |  | 2250
AST Fact Sheet #2: Embedded Data Collector
- Interviews with AST principal(s) |  | 3 Hours
- Research |  | 3 Hours
- Content Planning |  | 1 Hour
- Writing and Editing |  | 8 Hours
Subtotal | 15 Hours at $150/Hour |  |  | 2250
AST Fact Sheet #3: Low Profile Barrier System
- Interviews with AST principal(s) |  | 3 Hours
- Research |  | 3 Hours
- Content Planning |  | 1 Hour
- Writing and Editing |  | 8 Hours
Subtotal | 15 Hours at $150/Hour |  |  | 2250
Design/Graphics (All Three ASTs)
- Artwork
- Layout
- PDF Preparation
- Web Design and Formatting (including appropriate links)
Subtotal | 8 Hours at $150/Hour |  |  | 1200
|  |  | TOTAL: | 7950

## SPMT
[7 empty] | Proposed Budget | [6 empty] | Actual Costs
[7 empty] | FY08 |  | FY09 |  | FY10 |  | Subtotals of Costs to AASHTO | FY08 |  | FY09 |  | FY10
Cost Type/Description | Cost | Location (FY08) | Locations (FY09) | Locations (FY10) | Number of team members | Estimated Non-reimbursed Costs to Lead States** | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO |  | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO
Promotional Material
Brochure | [6 empty] | 1000 | 2000 |  |  |  |  | 3000
Website | [12 empty] | 0
PPT | [6 empty] | 2000 | [5 empty] | 2000
E-Mail Blast (1) | [8 empty] | 150 | 500 |  |  | 650
Trade Journal Articles (1) | [6 empty] | 3000 | [5 empty] | 3000
Surveys (2) | [12 empty] | 0
Total Promotional Material | [5 empty] | 0 | 6000 | 2000 | 150 | 500 | 0 | 0 | 8650
Operating and Other Expenses | [12 empty] | 0
Travel for Task 1: a) 4 trips for presentations at key meetings/conferences x 1 LST member | 1200 | 1 | 2 | 1 | 1 |  |  | 1200 |  | 2400 |  | 1200 | 4800
b) 10 trips to target States x 2 LST members during project period | 1200 | 3 | 3 | 4 | 2 |  |  | 7200 |  | 7200 |  | 9600
c) 1 LST member to TRB meeting for presentation; plus State agency paid travel for additional representative | 1200 | 1 |  |  | 1 |  |  | 1200 |  | 0 |  | 0
Travel for Task 2: 5 trips x 1 LST members for technical assistance to States | 1200 | 3 | 2 |  | 1 |  |  | 3600 |  | 2400 |  | 0 | 6000
Travel for Task 3: 5 trips x 1 LST members for technical assistance to Local agencies/MPO's/toll facilities | 1200 | 3 | 2 |  | 1 |  |  | 3600 |  | 2400 |  | 0 | 6000
Travel for interim LST team meeting x 5 LST members | 1200 |  | 1 |  | 5 |  |  | 0 |  | 6000 |  | 0 | 6000
Expenses for interim LST team meeting (meeting room rental, food, etc.) | [9 empty] | 2000 |  | 0 | 2000
Expenses for initial LST team meeting | [7 empty] | 10000 |  |  |  |  | 10000
Expense for marketing plan development | [6 empty] | 4500 | [5 empty] | 4500
Expense for ongoing marketing support & counsel | [6 empty] | 3000 |  | 3000 |  | 3000 |  | 9000
LST Conference Calls/E-Communications
Total Operating/Other Expenses | [5 empty] | 0 | 7500 | 26800 | 3000 | 22400 | 3000 | 10800 | 73500
Expendable Goods & Supplies | [12 empty] | 0
Long Distance Telephone Charges | [7 empty] | 250 |  | 250 |  | 250 | 750
Reproduction | [7 empty] | 250 |  | 250 |  | 250 | 750
Shipping | [7 empty] | 250 |  | 250 |  | 250 | 750
Equipment Rental | [7 empty] | 250 |  | 250 |  | 250 | 750
Total Expendable Goods & Supplies | [5 empty] | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 3000
Equipment Purchase
Total Equipment Purchase | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontracts*
Bridge/Structures Consultant (Ralls) | [6 empty] | 2500 |  | 2500 |  | 2500
Total Subcontractors
Total Lead States Contribution | [5 empty] | 0
Total AASHTO Request | [6 empty] | 13500 | 29800 | 3150 | 23900 | 3000 | 11800 | 85150
[7 empty] | FY 08 Total | 43300 | FY 09 Total | 27050 | FY 10 Total | 14800
*Subcontracts should be established directly with AASHTO. Contact the AASHTO TIG Program Manager for assistance.
**Estimated labor and travel costs for 3-year performance period.
Notes:
1. The proposed AASHTO reimbursed budget is not to include salary and fringe benefits for lead states team members providing services.
2. Travel expenses for lead states team members reprenting industry are not reimbursable by AASHTO.
3. Appropriate indirect charges may be included in the individual cost estimates above.

## AMG
[8 empty] | Proposed Budget | [6 empty] | Actual Costs
[8 empty] | FY08 |  | FY09 |  | FY10 |  | Subtotals of Costs to AASHTO | FY08 |  | FY09 |  | FY10
Cost Type/Description | Cost | Locations (FY08) | Locations (FY09) | Locations (FY10) | Number of trips/yr | Number of team members | Estimated Non-reimbursed Costs to Lead States | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO |  | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO | Labor Costs to be Reimbursed by AASHTO | Direct Costs to be Reimbursed by AASHTO
Promotional Material
Brochure | [6 empty] | 2750 | 700 | 2000 |  |  |  |  | 2700
Website | [6 empty] | 2250 | [6 empty] | 0
PPT | [6 empty] | 3000 | 300 | [5 empty] | 300
E-Mail Blast (1) | [7 empty] | 150 | 500 | 150 | 500 | 150 | 500 | 1950
Trade Journal Articles (1) | [6 empty] | 3225 | 0 | [5 empty] | 0
Surveys (2) | [6 empty] | 27000 | [6 empty] | 0
Total Promotional Material | [6 empty] | 38225 | 1150 | 2500 | 150 | 500 | 150 | 500 | 4950
Operating and Other Expenses | [13 empty] | 0
Travel for Task 1: Visit 6 target States 2x each during project period, plus additional States/trips as needed to meet goal; 2 LST members toTRB meeting for presentation; plus State agency paid travel for additional representatives | 1200 | 4 | 2 | 2 | 2 | 2 | 86400 |  | 19200 |  | 9600 |  | 9600 | 38400
Travel for Task 3: 2 workshops/year in FY 08 and 09 (using webinars/electronic media, if possible) | [6 empty] | 12300 |  | 0 |  | 0 |  |  | 0
Travel for Task 4: national/regional meetings for presentations to contractors; plus agency-paid travel for additional representatives | 1200 | 1 | 1 |  | 1 | 1 | 3600 |  | 1200 |  | 1200 |  |  | 2400
Travel for Task 7: national/regional meetings for presentations to agency personnel; plus agency-paid travel for additional representatives | 1200 | 1 | 1 |  | 1 | 1 | 97200 |  | 1200 |  | 1200 |  |  | 2400
Travel for interim LST team meeting, plus agency-paid travel for additional LST members | 1200 |  | 1 |  | 1 | 7 | 34800 |  |  |  | 8400 |  |  | 8400
Expenses for interim LST team meeting (meeting room rental, food, etc.) | [6 empty] | TBD | [6 empty] | 0
Expenses for initial LST team meeting | [6 empty] | 27600 |  | 10000 |  |  |  |  | 10000
Expense for marketing plan development | [7 empty] | 4500 | [5 empty] | 4500
Expense for ongoing marketing support & counsel | [6 empty] | 7500 | 3000 |  | 3000 |  | 3000 |  | 9000
Development of inspection technician QA/QC guidance for TIG/AMG website | [6 empty] | 93000 | [6 empty] | 0
Total Operating/Other Expenses | [6 empty] | 362400 | 7500 | 31600 | 3000 | 20400 | 3000 | 9600 | 75100
Expendable Goods & Supplies | [13 empty] | 0
Long Distance Telephone Charges | [6 empty] | TBD |  | 250 |  | 250 |  | 250 | 750
Reproduction | [6 empty] | TBD |  | 250 |  | 250 |  | 250 | 750
Shipping | [8 empty] | 250 |  | 250 |  | 250 | 750
Equipment Rental | [6 empty] | TBD |  | 250 |  | 250 |  | 250 | 750
Total Expendable Goods & Supplies | [6 empty] | 0 | 0 | 1000 | 0 | 1000 | 0 | 1000 | 3000
Equipment Purchase
TBD | [6 empty] | TBD
Total Equipment Purchase | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Subcontracts*
TBD
Total Subcontractors
Total Lead States Contribution | [6 empty] | 400625
Total AASHTO Request | [7 empty] | 8650 | 35100 | 3150 | 21900 | 3150 | 11100 | 83050
[8 empty] | FY 08 Total | 43750 | FY 09 Total | 25050 | FY 10 Total | 14250
*Subcontracts should be established directly with AASHTO. Contact the AASHTO TIG Program Manager for assistance.
Notes:
1. The proposed AASHTO reimbursed budget is not to include salary and fringe benefits for lead states team members providing services.
2. Travel expenses for lead states team members reprenting industry are not reimbursable by AASHTO.
3. Appropriate indirect charges may be included in the individual cost estimates above.